## Data
Site Reference | Site Name | LDP reference | Site Address | Easting | Northing | Site Area (Hectares) | Year Added To HLA | LDP / Windfall / Other | Planning Status | Other detail | Main Planning Application Reference(s) | Planning Approval Date | Construction status | Year construction started | Site Capacity | Remaining capacity | Completions in the Audit Year | Total completions to date | Programming_Y1 | Programming_Y2 | Programming_Y3 | Programming_Y4 | Programming_Y5 | Programming_Y6 | Programming_Y7 | Programming_Y8 | Programming_Y9 | Programming_Y10 | Pipeline Timeframe | Tenure | Number Market | Number Affordable | Number flats | Number houses | Deliverability status | Constraint notes | Action required | Owner | Developer | Greenfield / Brownfield | VDL | Self Build | Dispute | Demolition | Programming note
WD0355A | LITTLEMILL DISTILERY (NORTH EAST) | H2(62) | LITTLEMILL DISTILERY (NORTH EAST), BOWLING | 244133 | 673777 | 0.45 | 1996 | LDP | No Consent | Landowner responded to 2026 Developer Intention Survey | 03/334 |  | Not yet started |  | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 33 | - |  |  | Constrained | Physical: high risk of surface water flooding. Some buildings on site require demolition, however consent is in place to do so. | Landowner to undertake demolition of existing building onsite and apply for planning permission. Planning authority to continue to monitor site. | Private Owner | NK | Brownfield | Yes |  | No dispute |  | Landowner indicated short term delivery, however there are is not planning consent or application and that buildings on the site require demolition the site.deliverability status was changed to constrained following discussion with HfS due to high risk of surface water and/or small watercourse flooding.
WD0392 | 354-394 DUMBARTON ROAD | H2(51) | 354-394 DUMBARTON ROAD, CLYDEBANK | 248943 | 670790 | 0.17 | 1999 | LDP | No Consent | In 2025 Electronic advertising boards erected on site. |  |  | Not yet started |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | - | 10 |  |  | Constrained | Ownership: Erection of electronic billboards indicates lack of intention to develop in short term. | Planning authority to continue to monitor site and seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Brownfield | Yes |  | No dispute |  | Programming removed following discussion with HfS and site no longer in SHIP
WD0401 | CRAIGEND HOUSE, CARDROSS ROAD | H2(22) | CRAIGEND HOUSE, CARDROSS ROAD, DUMBARTON | 238217 | 675630 | 4.96 | 1998 | LDP | Consented (full) | Under construction | DC/21/211/FUL | 2022-09-14 | Started on site |  | 81 | 49 | 32 | 32 | 38 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 81 | - |  |  | Deliverable | No known constraints | Developer to continue progressing site Planning Authority to continue to monitor site. | Private Owner | MILLER HOMES | Brownfield | Yes |  | No dispute |  | Programming adjusted to reflect lower than expected completions in the audit year. Remainder added on to 2027/28
WD0427A | KEIL SCHOOL PHASE 2 | H2(20) | KEIL SCHOOL PHASE 2, DUMBARTON | 238664 | 675110 | 1.54 | 2001 | LDP | No Consent | Landowner seeking solutions for delivering the site |  |  | Not yet started |  | 51 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 51 | - |  |  | Constrained | Constraints Unknown | Site owner currnetly investigating site constraints. Planning Authority and owner to continue discussions as necessary. Planning Authority to continue to monitor site. | Private Owner | NK | Brownfield | No |  | No dispute
WD0450 | HARDGATE HALL | H2(28) | HARDGATE HALL, HARDGATE | 249761 | 672859 | 0.1 | 2005 | LDP | Consented (full) |  | DC20/121 | 2020-10-08 | Started on site |  | 5 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 5 | - |  |  | Deliverable | No known constraints | Planning authority to continue to monitor site. | Private Owner | NK | Brownfield | No |  | No dispute
WD0463A | QUEENS QUAY - EAST YARD | H2(11) | QUEENS QUAY - EAST YARD, CLYDEBANK | 249760 | 669781 | 4.28 | 2003 | LDP | Consented (PPiP) |  | DC15/234 | 2016-08-28 | Not yet started |  | 344 | 344 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | Short-term | Market | 344 | - |  |  | Deliverable with Constraints | Financial: industry are citing issues with the marketability of the site. | Planning authority and developer to work together to progress planning application. | Private Owner | NK | Brownfield | Yes |  | Disputed by Homes for Scotland |  | Dispute maintained
WD0463B | QUEENS QUAY - PLOTS 8-12 | H2(11) | QUEENS QUAY - PLOTS 8-12, CLYDEBANK | 249377 | 670039 | 8.53 | 2003 | LDP | Consented (PPiP) |  | DC15/234 | 2016-08-28 | Not yet started |  | 468 | 468 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | Short-term | Market | 468 | - |  |  | Deliverable with Constraints | Financial: industry are citing issues with the marketability of the site. | Planning authority and developer to work together to progress planning application. | Private Owner | NK | Brownfield | No |  | Disputed by Homes for Scotland |  | Dispute maintained
WD0463C | QUEENS QUAY - PLOT 7 | H2(49) | QUEENS QUAY - PLOT 7, CLYDEBANK | 249380 | 670232 | 2.6 | 2003 | LDP | Consented (PPiP) | SHIP site. Capacity changed from 98 to 100 to reflect SHIP @2024. @2025 - No longer ship site, programming moved back a year | DC15/234 | 2016-08-28 | Not yet started |  | 100 | 100 | 0 | 0 | 0 | 0 | 30 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 100 |  |  | Deliverable with Constraints | Financial: industry are citing issues with the marketability of the site. | Planning authority and developer to work together to progress planning application. | Mixed ownership | WDC | Brownfield | Yes |  | Disputed by Homes for Scotland |  | Dispute maintaned
WD0476 | CARLESS OIL DEPOT | H2(33) | CARLESS OIL DEPOT, OLD KILPATRICK | 246884 | 671939 | 11.77 | 2004 | LDP | No Consent | 2010 plan has larger site identified with capacity of 400. 2020 plan identifies smaller part of site for 50 units. |  |  | Not yet started |  | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 50 | - |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. Physical: currently no adoptable vehical access to site. Potential contamination. | Planning authority continue to monitor site delivery | Private Owner | NK | Brownfield | No |  | No dispute
WD0477 | THOR CERAMICS STANFORD ST | H2(14) | THOR CERAMICS STANFORD ST, CLYDEBANK | 250202 | 670241 | 1.34 | 2004 | LDP | No Consent | @ 2026 HfS informed council that site is currently being marketed. |  |  | Not yet started |  | 92 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 92 | - |  |  | Constrained | Land Use Status: Allocated in LDP2 but no active planning permission. | Planning authority to continue to monitor site. | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0479 | AULD STREET Ph 2 | H2(52) | AULD STREET Ph 2, DALMUIR | 248387 | 671008 | 0.4 | 2004 | LDP | Consented (full) | 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme. | DC21/291/FUL | 2025-10-09 | Not yet started |  | 32 | 32 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 32 |  |  | Deliverable | 0 | Planning Authority to continue to monitor site | Private Owner | DALMUIR HOUSING ASSOCIATION | Brownfield | Yes |  | No dispute |  | Programming from SHIP
WD0482 | SHED 7 CASTLE RD |  | SHED 7 CASTLE RD, DUMBARTON | 240286 | 674623 | 5.08 | 2005 | Windfall | Consented (full) | At march 2023, Phases 1 & 2 complete. Phase 3 comprises 6 flatted blocks and 16 houses. 16 houses complete. Block 4 complete and partially occupied (5 units at May 2023). Blocks 5 & 6 well out of the ground. Blocks 7,8 & 9 at founds. At September 2024 Block 5 complete and mostly occupied, with remaining flats able to be occupied. For sale signs in block 6 and some signs of occupation, however internal works taking place in some flats. Block 7 construction underway. 8 and 9 not yet beyond foundations. At 2025 Final two blocks of flats under construction (blocks 8 and 9) and emaining flats ready for occupation. At 2026 block 8 mostly complete and block 9 under construction. | DC19/096 | 2019-10-23 | Started on site |  | 219 | 14 | 16 | 205 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 219 | - |  |  | Deliverable | No known constraints | Planning Authority continue to monitor site delivery | Private Owner | TURNBERRY HOMES | Brownfield | No |  | No dispute |  | Programming agreed with Turnburry
WD0489 | CABLE DEPOT ROAD SOUTH | H2(9) | CABLE DEPOT ROAD SOUTH, CLYDEBANK | 249146 | 670354 | 3.26 | 2005 | LDP | No Consent |  |  |  | Not yet started |  | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 200 | - |  |  | Constrained | Land Use Status: Site is allocated in LDP2 but does not have planning permission Financial: industry are citing issues with the marketability of the site. | Seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0494 | CARLEITH | H2(25) | CARLEITH, CLYDEBANK | 248123 | 673121 | 0.67 | 2006 | LDP | No Consent | 2026 Construction underway on two dwellings. Capacity changed to 2 to reflect implimented permission. While implimented permission is below the threshold for tracking in the HLA (4 dwellings) the site will be continued to be monitored as it is an allocation in LDP2. |  |  | Started on site |  | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 2 | - |  |  | Deliverable | No known constraints | Planning Authority continue to monitor site delivery | Private Owner | PLOTS | Brownfield | No |  | No dispute |  | Programming assumed from site activity
WD0501 | LEVENBANK STREET |  | LEVENBANK STREET, JAMESTOWN | 239821 | 681066 | 2.86 | 2006 | Windfall | No Consent | Site has been marketed and is currently under offer. Site is accessed by an unadoppted road, however the road is also owned by the council. Discussions with Road and planning services taking place to resolve this. Pre-app discussions have taken place |  |  | Not yet started |  | 86 | 86 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 30 | 6 | 0 | 0 | 0 |  | Market | 86 | - |  |  | Deliverable with constraints | Land Use Status: Allocated in LDP but no active planning permission. Ownership: Disucssions taking place between owner (Council) and potential developer. Physical: Access road is not adopted | Council and developer to conclude purchase of site. Council and developer to agree access solution | West Dunbartonshire Council | NK | Greenfield | No |  | No dispute |  | Programming assumed. Medium term delivery assumed based on current stage of pre-app discussions and land sale negotiations, developers previous delivery rates and assumed delivery rates on other sites.
WD0518A | HEATHER AVENUE - REMAINDER | H2(2) | HEATHER AVENUE - REMAINDER, ALEXANDRIA | 239198 | 680603 | 2.51 | 2007 | LDP | No Consent |  |  |  | Not yet started |  | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 84 | - |  |  | Constrained | Physical: Some areas of site at risk of flooding - however significant portion of the site under no risk from flooding Land Use Status: Allocated in LDP2, but no active planning permission | Planning authority to continue to monitor site. | West Dunbartonshire Council | NK | Brownfield | Yes |  | No dispute
WD0524 | 14-20 GOLFHILL DRIVE | H2(48) | 14-20 GOLFHILL DRIVE, BONHILL | 239865 | 680262 | 0.1 | 2006 | LDP | Consented (full) | 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme. | DC22/154/FUL | 2023-11-07 | Not yet started |  | 7 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 7 |  |  | Deliverable | No known constraints | Planning authority to continue to monitor site. | Housing Association | DUNBRITTON HA | Brownfield | No |  | No dispute |  | Programming from SHIP
WD0528 | N DOUGLAS ST/FORMER UNITY CLUB | H2(10) | N DOUGLAS ST/FORMER UNITY CLUB, CLYDEBANK | 250197 | 669660 | 0.06 | 2008 | LDP | No Consent |  | DC07/207/FUL |  | Not yet started |  | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 12 | - |  |  | Constrained | Constraints unknown | Planning authority to continue to monitor site. | Private Owner | NK | Brownfield | No |  | No dispute
WD0541 | LEVENBANK ROAD | H2(29) | LEVENBANK ROAD, JAMESTOWN | 239940 | 681194 | 2.18 | 2009 | LDP | No Consent |  |  |  | Not yet started |  | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 60 | - |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. | Planning authority to continue to monitor site. Seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | NK | Greenfield | Yes |  | No dispute
WD0544 | BOQUHANRAN ROAD | H2(53) | BOQUHANRAN ROAD, CLYDEBANK | 248939 | 670824 | 0.8 | 2009 | LDP | No Consent | @ 2025 site removed from SHIP. Programming removed |  |  | Not yet started |  | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | - | 34 |  |  | Constrained | Financial: Currently lacks funding commitment to deliver the site. It has been removed from SHIP. Land Use Status: Site is allocated in LDP2, but no active planning permission | Planning authority to continue to monitor site. Seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | CLYDEBANK HA | Brownfield | Yes |  | No dispute |  | Site removed from SHIP . Programming Removed
WD0546 | MELBOURNE AVE/SALISBURY PL Phase 1 | H2(55) | MELBOURNE AVE/SALISBURY PL Phase 1, CLYDEBANK | 247840 | 672193 | 0.48 | 2010 | LDP | No Consent |  |  |  | Not yet started |  | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | - | 25 |  |  | Constrained | Physical: Steep slope Land Use Status: Site is allocated in LDP2, but no active planning permission | WDC Housing to seek developers to deliver site | West Dunbartonshire Council | NK | Brownfield | Yes |  | No dispute
WD0548 | LAND AROUND FOOTBALL STADIUM |  | LAND AROUND FOOTBALL STADIUM, DUMBARTON | 240069 | 674743 | 3.44 | 2010 | Windfall | No Consent | @2024 Mapping changed to improve accuracy DC19/127 Application pending - to extend permission and change to compliance with a condition on permission DC19/127. | DC19/127 | 2019-12-18 | Not yet started |  | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 37 | - |  |  | Removed | Land Use Status: No allocated in LDP. No active planning permission | Remove site from housing land audit. | Private Owner | NK | Brownfield | No |  | No dispute
WD0551 | FORMER COTTAGE HOSPITAL, PARK CRES | H2(59) | FORMER COTTAGE HOSPITAL, PARK CRES, DUMBARTON | 239960 | 676026 | 0.26 | 2011 | LDP | No Consent | Development brief prepared Site in 2026-31 SHIP, but not seen as deliverable within the short to medium term. |  |  | Not yet started |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Long-term | Affordable | - | 10 |  |  | Constrained | Financial: SHIP states that site is not deliverable within short to medium term due to funding availability. Land Use Status: Site is allocated in LDP2, but no active planning permission | WDC Housing seeking potential developers to bring the site forward. | West Dunbartonshire Council | NK | Brownfield | Yes |  | No dispute
WD0552 | OLD MILL GARAGE |  | OLD MILL GARAGE, HARDGATE | 249770 | 672885 | 0.44 | 2011 | Windfall | No Consent | Industrial unit under construction - remove from audit |  |  | Not yet started |  | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 12 | - |  |  | Removed | Land Use Status: Application pending for industrial unit. On site at time of audit. Physical: Site is at risk of flooding | Remove site from housing land audit. | Private Owner | NK | Brownfield | No |  | No dispute
WD0556 | MITCHELL WAY | H2(3) | MITCHELL WAY, ALEXANDRIA | 239156 | 680025 | 0.18 | 2012 | LDP | No Consent | 2023-2028SHIP site but with no capacity @ 2024 Flats along Mitchell Way have now been demolished and Lidl is under construction. A portion of the site remains, but capacity needs to be reassessed. Site in 2025-30 SHIP, but not seen as deliverable within the short to medium term. @ 2025 No progress made on the site. Site has been removed from SHIP |  |  | Not yet started |  | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | - | 26 |  |  | Constrained | Land Use Status: Allocated in LDP, but no active planning permission | Council to market site | West Dunbartonshire Council | NK | Brownfield | No |  | No dispute
WD0563 | RADNOR PARK HOTEL | H2(12) | RADNOR PARK HOTEL, CLYDEBANK | 249744 | 671544 | 0.31 | 2013 | LDP | No Consent | At 2026 site in SHIP as a reserved site. Site capacity changed to reflect planning application |  |  | Not yet started |  | 34 | 34 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 34 |  |  | Deliverable with constraints | Physical: Existing telecoms mast on site. Land use status: site is allocated in the LDP but does not yet have planning permission. | Planning Authority and landowner/developer to progress planning application Landowner/developer to progress removal of telecoms mast. | Private Owner | CRUDEN | Brownfield | No |  | No dispute |  | Programming provided by Cruden
WD0564 | BOWLING BASIN | H2(6) | BOWLING BASIN, BOWLING | 245290 | 673427 | 1.69 | 2013 | LDP | Consented (PPiP) | The non-housing element of the development has been implimented. The Planning Permission in Principle establishes the use on site. | DC15/270 |  | Not yet started |  | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 75 | - |  |  | Constrained | Ownership: Not clear if owner, Scottish Canals, intends to complete partially implimented permission | Planning Authority continue to monitor site | Private Owner | NK | Brownfield | No |  | No dispute
WD0565 | SCOTTS YARD | H2(7) | SCOTTS YARD, BOWLING | 244243 | 673632 | 2.32 | 2013 | LDP | No Consent |  |  |  | Not yet started |  | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 75 | - |  |  | Constrained | Physical: Site at high risk of coastal flooding. Access reliant on delivery of Exxon industrial redevelopment Land Use: Site is allocated in LDP2, but no active planning permission | Planning Authority continue to monitor site | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0570 | HILLVIEW | H2(31) | HILLVIEW, MILTON | 242672 | 674480 | 0.34 | 2014 | LDP | Consented (full) |  | 16/146 |  | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 4 | - |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. | Planning authority to continue to monitor site. Seek further information from site owner as to their intent with the site and any potential constraints | Private Owner | PLOTS | Brownfield | No |  | No dispute
WD0573 | SANDPOINT MARINA | H2(24) | SANDPOINT MARINA, DUMBARTON | 239759 | 674837 | 3.9 | 2014 | LDP | No Consent | Currently being used as a construction compound. Height of land has been increased significantly |  |  | Not yet started |  | 87 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 87 | - |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. Site currently under use as construction compound. Physical: Site at high risk of coastal flooding. | Planning Authority continue to monitor site | Private Owner | NK | Brownfield | No |  | No dispute
WD0575 | STANFORD STREET (COUNCIL DEPOT) | E4 | STANFORD STREET (COUNCIL DEPOT), CLYDEBANK | 250178 | 670135 | 2.12 | 2014 | LDP | No Consent | Council intends to market site in 2026/2027 financial year |  |  | Not yet started |  | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 120 | - |  |  | Constrained | Ownership: Site is still in use as a depot Land Use Status: Site allocated in LDP but no planning permission | Council is expected to market ite within the next financial year | West Dunbartonshire Council | NK | Brownfield | No |  | No dispute
WD0578 | HAWTHORNHILL ROAD | H2(23) | HAWTHORNHILL ROAD, DUMBARTON | 238306 | 675907 | 3.26 | 2015 | LDP | Consented (full) | Under construction. | DC22/072/FUL |  | Started on site |  | 68 | 31 | 24 | 37 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 68 | - |  |  | Deliverable | No known constraints | Developer to continue progressing site. Planning Authority continue to monitor site | Private Owner | PERSIMMON | Brownfield | Yes |  | No dispute |  | Programming agreed with Persimmon
WD0581 | COCHNO WATERWORKS |  | COCHNO WATERWORKS, HARDGATE | 249480 | 673823 | 0.67 | 2015 | Windfall | No Consent |  |  |  | Not yet started |  | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 11 | - |  |  | Constrained | No known constraints, however no works appear to have been carried out on site other than fencing site off | Planning Authority continue to monitor site | Private Owner | NK | Brownfield | Yes |  | No dispute
WD0588 | FORMER CLYDEBANK HEALTH CENTRE | H2(36) | FORMER CLYDEBANK HEALTH CENTRE, CLYDEBANK | 249714 | 671478 | 1.04 | 2016 | LDP | Consented (full) | Health centre has been demolished. 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme. Permission granted on site 2025/26 for 42 dwellings, 27 of which is for sheltered housing. Only the remaining 15 homes are inlcuded in the audit. | DC25/186/FUL | 2026-01-29 | Not yet started |  | 15 | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 15 |  |  | Deliverable | No known constraints | Developer to continue progressing site. Planning Authority continue to monitor site | Other Owner | WDC | Brownfield | No |  | No dispute |  | Programming from SHIP
WD0591 | adj 102 EAST BARNS STREET | H2(15) | adj 102 EAST BARNS STREET, CLYDEBANK | 250853 | 669380 | 0.07 | 2017 | LDP | Consented (full) | Permission lapsed in 2025 | DC19/141 | 2020-12-23 | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 4 | - |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission | Planning Authority continue to monitor site | Private Owner | NK | Brownfield | No |  | No dispute
WD0592 | CROSSLET ESTATE | H2(17) | CROSSLET ESTATE, DUMBARTON | 241202 | 675350 | 0.74 | 2017 | LDP | No Consent | Pre-app discussions have taken place with applicant |  |  | Not yet started |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | Medium-term | Market | 6 | - |  |  | Deliverable with constraints | Physical: Site is steeply sloped Land Use Status: Site is allocated in LDP2 but does not have planning permission | Developer to continue progressing site. Planning Authority continue to monitor site | West Dunbartonshire Council | PLOTS | Greenfield | No |  | No dispute
WD0593 | CHURCH STREET FORMER COUNCIL OFFICE | H2(35) | CHURCH STREET FORMER COUNCIL OFFICE, ALEXANDRIA | 239194 | 679890 | 0.26 | 2018 | LDP | No Consent | Site has been sold by WDC and being retained as serviced accomodation. |  |  | Not yet started |  | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 15 | - |  |  | Constrained | Ownership: Business uses still on site. Recent planning application to change from class 4 (office) to business centre (Sui generis) indicates there is no intent to deliver housing on the site. Land Use Status: Allocated in LDP but no planning permission | Planning authority to continue to monitor site. | Private Owner | NK | Brownfield | No |  | No dispute
WD0594 | HARDGATE HEALTH CENTRE | H2(37) | HARDGATE HEALTH CENTRE, HARDGATE | 249732 | 672562 | 0.13 | 2018 | LDP | No Consent |  |  |  | Not yet started |  | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 6 | - |  |  | Constrained | Ownership: No steps taken to progress site since closure of health centre. Land Use Status: Allocated in LDP but no planning permission | Planning Authority continue to monitor site | Other Owner | NK | Brownfield | No |  | No dispute
WD0596 | MAIN STREET | H2(40) | MAIN STREET, JAMESTOWN | 239680 | 681224 | 0.19 | 2018 | LDP | No Consent |  |  |  | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Market | 4 | - |  |  | Constrained | Land Use Status: Allocated in LDP but no active planning permission. | Planning Authority to continue to monitor site. | Private Owner | NK | Greenfield | Yes |  | No dispute
WD0597 | GLEBE | H2(41) | GLEBE, OLD KILPATRICK | 246305 | 672932 | 1.08 | 2018 | LDP | No Consent |  |  |  | Not yet started |  | 15 | 15 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 15 | - |  |  | Deliverable with constraints | Land Use Status: Allocated in LDP but no active planning permission. Physical: Surface water flooding | Landowner has engaged consultants to address surface water issues. Planning Authority to continue to monitor site. | Private Owner | NK | Greenfield | No |  | Disputed by Homes for Scotland |  | Landowner indicated delivery of the whole site in 2026/2027. As the site currently has no applications granted or being determined an additional two years has been added to the programming.
WD0598 | FAIFLEY BOWLING CLUB | H2(63) | FAIFLEY BOWLING CLUB, FAIFLEY | 250419 | 672935 | 1.02 | 2018 | LDP | Consented (full) | 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme.. Programming from SHIP. @2024 capacity updated to match planning permission | DC23/083/FUL | 2023-10-14 | Not yet started |  | 27 | 27 | 0 | 0 | 0 | 14 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 27 |  |  | Deliverable with constraints | Physical: steep slope on site Financial: Govenrment funding for delivery of affordable housing required. | Developer to continue discussions with Scottish Government Planning Authority to continue to monitor site. | West Dunbartonshire Council | KNOWES HA | Brownfield | No |  | No dispute |  | Programming from SHIP - however developer proposes whole site to be complete in 2027/28.
WD0599 | RHI SITE - STANFORD STREET | H2(38) | RHI SITE - STANFORD STREET, CLYDEBANK | 250490 | 670244 | 3.09 | 2018 | LDP | Consented (full) | Site programming changed to reflect response from developer to Developer Intentions Survey | DC19/186 |  | Started on site |  | 135 | 135 | 0 | 0 | 0 | 20 | 25 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | Short-term | Market | 135 | - |  |  | Deliverable | No known constraints | Developer to progress site Planning Authority to continue to monitor site. | Private Owner | TURNBERRY HOMES | Brownfield | No |  | No dispute |  | Programming provided by Turnburry
WD0603 | FRANK DOWNIE HOUSE |  | FRANK DOWNIE HOUSE, CLYDEBANK | 247765 | 671559 | 0.31 | 2020 | Windfall | Consented (full) | 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme. | DC25/144/FUL | 2025-11-19 | Not yet started |  | 21 | 21 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 21 |  |  | Deliverable | No known constraints | Developer to progress site Planning Authority to continue to monitor site. | Private Owner | CCG | Brownfield | No |  | No dispute |  | Programming from SHIP
WD0604 | DICKENS AVENUE |  | DICKENS AVENUE, CLYDEBANK | 248910 | 671680 | 0.03 | 2020 | Windfall | No Consent | @2025 Discussions taking place between landowner (council) and developer. At 2026 site programming adjusted to reflect information from Developer Intentions Survey |  |  | Not yet started |  | 22 | 22 | 0 | 0 | 0 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 22 | - |  |  | Deliverable with constraints | Land Use Status: Allocated in LDP but no active planning permission Physical: Site slopes steeply | Council and developer to conclude sale of site. Developer identify solution to slope of site and to progress planning application Planning Authority to continue to monitor site. | West Dunbartonshire Council | TURNBERRY HOMES | Brownfield | No |  | Disputed by Homes for Scotland |  | Programming provided by Turnburry
WD0605 | QUEEN MARY DAY CARE CENTRE |  | QUEEN MARY DAY CARE CENTRE, CLYDEBANK | 250650 | 670790 | 0.3 | 2020 | Windfall | Consented (full) | 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme. @2025 capacity changed to reflect SHIP. | DC25/033/FUL | 2025-06-26 | Started on site |  | 17 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 17 |  |  | Deliverable | No known constraints | Planning Authority to continue to monitor site. | West Dunbartonshire Council | WDC | Brownfield | No |  | No dispute |  | Programming from SHIP
WD0608 | BELLSMYRE REDEVELOPMENT, PHASES 1-3 |  | BELLSMYRE REDEVELOPMENT, PHASES 1-3, DUMBARTON | 240847 | 676542 | 4.87 | 2022 | Windfall | Consented (full) | Phase 1 complete. Pase 2 undertway. Demolitions on phase 3 have taken place. 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme. | DC21/244/FUL | 2022-02-16 | Started on site |  | 138 | 111 | 27 | 27 | 34 | 16 | 28 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 138 |  |  | Deliverable | No known constraints | Developer to continue progressing site Planning Authority to continue to monitor site. | Housing Association | CALEDONIA HA | Brownfield | No |  | No dispute |  | Programming from combinaiton of SHIP and Developer Intention Survey
WD0611 | DUNTIGLENNAN, FARM ROAD |  | DUNTIGLENNAN, FARM ROAD, CLYDEBANK | 248821 | 673368 | 8.84 | 2022 | Windfall | Consented (full) | @2025 site progressing. Completions and programming information provided by developer | DC22/049/MSC | 2023-01-31 | Started on site |  | 99 | 85 | 14 | 14 | 48 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 99 | - |  |  | Deliverable | No known constraints | Developer to continue progressing site Planning Authority to continue to monitor site. | Private Owner | BARRATT HOMES | Greenfield | No |  | No dispute |  | Programming provided by Barratt
WD0612 | FORMER PLAYDROME SITE |  | FORMER PLAYDROME SITE, CLYDEBANK | 249100 | 670200 | 3.56 | 2023 | Windfall | Consented (full) | @2025 Homes under construction. Foundations laid for first block and some walls going up @2024 capacity updated to match planning permission | DC23/149/FUL | 2024-04-15 | Started on site |  | 128 | 83 | 45 | 45 | 54 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 128 | - |  |  | Deliverable | No known constraints | Developer to continue progressing site Planning Authority to continue to monitor site. | West Dunbartonshire Council | MILLER HOMES | Brownfield | Yes |  | No dispute |  | Programming based on expected completion numbers provided in the previous audit and actual completions in the current audit year.
WD0614 | BONHILL GAP SITE CAMBELL STREET |  | BONHILL GAP SITE CAMBELL STREET, BONHILL | 239673 | 679549 | 0.24 | 2025 | Windfall | Consented (full) | 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme.. | DC24/080/FUL | 2024-09-01 | Started on site |  | 11 | 11 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 11 |  |  | Deliverable | No known constraints | Developer to continue progressing site Planning Authority to continue to monitor site. | West Dunbartonshire Council | WDC | Greenfield | No |  | No dispute |  | Programming from SHIP
WD0615 | BONHILL GAP SITE BRAEHEAD |  | BONHILL GAP SITE BRAEHEAD, BONHILL | 240633 | 679077 | 0.74 | 2025 | Windfall | Consented (full) | 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme. | DC24/096/FUL | 2025-01-31 | Started on site |  | 17 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 17 |  |  | Deliverable | No known constraints | Developer to continue progressing site Planning Authority to continue to monitor site. | West Dunbartonshire Council | WDC | Greenfield | No |  | No dispute |  | Programming from SHIP
WD0616 | BONHILL GAP SITE O'HARE |  | BONHILL GAP SITE O'HARE, BONHILL | 240279 | 679439 | 0.19 | 2025 | Windfall | Consented (full) | 2026-31 SHIP priority site with fundng from Affordable Housing Supply Programme. | DC24/161/FUL | 2025-03-04 | Not yet started |  | 6 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 6 |  |  | Deliverable | No known constraints | Planning Authority to continue to monitor site. | West Dunbartonshire Council | WDC | Greenfield | No |  | No dispute |  | Programming from SHIP
WDDB0300A | DALQUHURN | H2(61) | DALQUHURN, RENTON | 239195 | 677748 | 2.56 | 1991 | LDP | Consented (full) | 2025/30 SHIP priority site (SHOWS CAPACITY OF PHASES 5 & 6 AS 50). 2026/31 SHIP lists site as a reserve site and notes the site requires a new masterplan to continue. | DC08/033/FUL | 2008-06-03 | Started on site |  | 125 | 125 | 0 | 0 | 0 | 0 | 50 | 50 | 25 | 0 | 0 | 0 | 0 | 0 | Short-term | Affordable | - | 125 |  |  | Deliverable with constraints | Financial: Scottish Govenrment affordable housingh funding required. | Housing Assosciation to seek funding from Affordable Housing Supply Programme with support from WDC Housing. Planning Authority to continue to monitor site | Housing Association | CORDALE HA | Brownfield | No |  | No dispute |  | Programming from Developer
WDDB0300D | DALQUHURN PHASE 4 | H2(61) | DALQUHURN PHASE 4, RENTON | 239195 | 677748 | 0.7 | 1996 | LDP | Consented (full) | 2025/30 SHIP priority site, notes completion at September 2025. Grant from Affordable Housing Supply Programme. Completed homes are occupied. Remaining homes near completion with heras fence still around them. Signs of construction traffic and works internally are taking place. | DC18/233 | 2019-06-03 | Started on site |  | 25 | 0 | 18 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Affordable | - | 25 |  |  | Removed |  | Planning Authority to remove from audit | Housing Association | CALEDONIA HA | Brownfield | No |  | No dispute |  | Programming from SHIP
WDDB0302A | FORMER LEVEN SHIPYARD | H2(18) | FORMER LEVEN SHIPYARD, DUMBARTON | 240070 | 674903 | 3 | 1991 | LDP | Consented (full) | 2023 - split this from completed part of site to just leave balance of development land. 2026 - capacity updated to reflect new permission | 16/229 | 2025-12-17 | Not yet started |  | 134 | 134 | 0 | 0 | 0 | 12 | 27 | 30 | 30 | 35 | 0 | 0 | 0 | 0 | Short-term | Market | 134 | - |  |  | Deliverable | No known constraints. | Developer to continue progressing site. Planning Authority to continue to monitor site. | Private Owner | TURNBERRY HOMES | Brownfield | Yes |  | No dispute |  | Programming agreed with Turnburry
WD0620 | FORMER BALLOCH LIBRARY |  | FORMER BALLOCH LIBRARY, BALLOCH | 239658 | 681773 | 0.09 | 2026 | Windfall | Consented (full) | 2026 - site fenced off and skip presnet, indicating works have begun. | DC/25/065/FUL | 2026-01-29 | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 4 | - |  |  | Deliverable | No known constraints. | Developer to continue progressing site. Planning Authority to continue to monitor site. | Private Owner | 0 | Brownfield | No |  | No dispute |  | Programming assumed
WD0617 | FORMER ROUNDABOUT INN |  | FORMER ROUNDABOUT INN, BALLOCH | 239718 | 681713 | 0.22 | 2026 | Windfall | Consented (full) | 2026 - Hotel has been demolished | DC23/127/FUL | 2026-02-20 | Not yet started |  | 15 | 15 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 15 | - |  |  | Deliverable | No known constraints. | Developer to continue progressing site. Planning Authority to continue to monitor site. | Private Owner | 0 | Brownfield | No |  | No dispute |  | Programming assumed
WD0618 | ST MUNGOS EPISCOPAL CHURCH |  | ST MONGOS EPISCOPAL CHURCH, ALEXANDRIA | 238921 | 679549 | 0.19 | 2026 | Windfall | Consented (full) | Programming assumed | DC25/075/FUL | 2026-05-23 | Not yet started |  | 4 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 4 | - |  |  | Deliverable | No known constraints. | Developer to continue progressing site. Planning Authority to continue to monitor site. | Private Owner | 0 | Brownfield | No |  | No dispute |  | Programming assumed
WD0619 | FORMER GARSHAKE WATERWORKS |  | FORMER GARSHAKE WATERWORKS, DUMBARTON | 241567 | 676328 | 0.74 | 2026 | Windfall | Consented (PPiP) | Programming assumed | DC25/057/PPP | 2025-08-22 | Not yet started |  | 9 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short-term | Market | 9 | - |  |  | Deliverable | Land Use Status: permission in principle, however further applications required for detailed design Physical: demolitiion of existing buildings on site to take place. Potential land contamination | Developer to submit Matters Specified by Conditions applications Planning Authority to continue to monitor site. | Private Owner | 0 | Brownfield | No |  | No dispute |  | Programming assumed - landowner suggested completions in 2026/27, however matters specified by condition applications to be submitted and buildings on site to be demolished.